**Project Status Report II**

|  |
| --- |
| Date of Report Issue/Prepared: Jan 31st, 2019 |

Report Prepared By: Tamara Saldina

Employer/Organization: ITHD

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | ITHD | |
| T\_06 | |
| Start Date: **Jan 19, 2019** | End Date: **Feb 01, 2019** |
| Green (Good) - Yellow (Warning) - Red (Bad) | |

Summary:

|  |
| --- |
| **Project Status Summary** |
| The status report found within this document highlights the progress made thus far in the ITHD web application project. It outlines current accomplishments and achieved objectives (such as front-end polish) as well as the tasks and next steps to be implemented. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Migrations | Connectinglocal copy of the database to the desktop application |
| Polished front-end for both desktop application and web application |  |
| Authorization integration |  |
| Guards implementation |  |
| Redirection |  |
| 10 User controls for the desktop app |  |
| Creating local copy of the DB, connecting it to the desktop app (development phase only) |  |

Upcoming Objectives for Feb 2, 2019 to Mar 8, 2019

|  |  |  |  |
| --- | --- | --- | --- |
| **Planned Activities/Tasks for Next Period** | | | |
| Activity/Task | Assigned To | Duration | Date |
| Add more fields to the registration page to fit on our logic | Tamara | 1 week | Feb 2 - Feb 9 |
| Prepare graphic design styles | Ana | 1 week | Feb 9 - Feb 16 |
| Meet with the stakeholder in order to clarify the logic | Team | 4 hours | Feb 8 |
| Admin side for the web application: list users and their proposals | Tamara | 2 weeks | Feb 2 - Feb 16 |
| Client side for the web application: list client’s proposals on the dashboard | Tamara | 2 weeks | Feb 16 - Feb 28 |
| Connect local database  to the desktop application | Morgan | 1 week | Feb 8 - Feb 15 |
| Implement adding a client to the desktop application database and generate a personalized token for registration | Jerome | 2 weeks | Feb 8 - Feb 15 |
| Have all the user controls connected to corresponding data members via ViewModels | Ana, Jordan | 2 weeks | Feb 2 - Feb 16 |

Upcoming Milestones for Feb 2, 2019 to Mar 8, 2019

|  |  |  |
| --- | --- | --- |
| **Milestones for Next Period** | | |
| Milestone (Objective) | Assigned To | Delivery Date |
| Meeting | Team | Feb 8 |
| Implement UI design for the desktop application | Ana, Jordan, Morgan | Feb 28 |
| Implement client friendly user experience design for the web application | Tamara, Jerome | Feb 28 |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Inconsistencies with previously determined requirements | Establish more clarification with the stakeholder | February 8th, 2019 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| In the upcoming meeting with the stakeholders, they might dislike the front-end | Med | Med | Remind the stakeholder that UI design comes later in the development process |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport2”.

For e.g. T29\_ProjectStatusReport2

This is a group submission i.e. one per group.

**Due Dates:**

**Sunday, February 03, 2019 (11:59 p.m.)**